## Instructions
TEAM NAME | SSAD 46
PROJECT NAME | Surrogate City Finder Tool
PROJECT MENTOR | Dr Vishal Garg
TEAM MEMBERS | Arushi Vashist
Akanksha
Ayush Tripathi
Dhruva Das
Siddharth Bhatore

## Team_Status
TEAM NAME | SSAD 46
PROJECT NAME | Surrogate City Finder Tool
PROJECT MENTOR | Dr Vishal Garg
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
Week 6 (sept 8- sept 14)
Learn ROR | Preparation | All | 4 |  | Ongoing
Role preferences | Coordination | All | 0.5 | 0.3 | Done |  | 0.2 | 66.6667
Bitbucket Repository | Preparation | All | 1 | 1.5 | Done |  | -0.5 | 33.3333
Develop Project plan Document | Documentation | Siddharth | 5 |  | Done
Meet and Discuss requirements with client | Preparation | All | 1.5 | 1 | Done |  | 0.5 | 50
Research Technology | Preparation | Arushi | 2 | 1.5 | Ongoing |  | 0.5 | 33.3333
Project synopsis writeup | Documentation | Dhruva | 2 | 2 | Done |  | 0 | 0
Identify role owners | Preparation | Ayush | 1 | 0.6 | Done |  | 0.4 | 66.6667
Team Meeting | Coordination | All | 1 | 2 | Done |  | -1 | 50
Status tracker | Documentation | All | 1 | 1 | Done |  | 0 | 0
Week 7 (sept 15 - sept 21)
Learn ROR | Preparation | All | 10 | 10 | Ongoing |  | 0 | 0
Testing Google Map APIs For Project | Testing | Arushi | 5 | 5 | Ongoing |  | 0 | 0
Software Requirements Specification Document | Requirements | Siddharth, Dhruv | 2 | 4 | Done |  | -2 | 50
Get Weather Data for Project | Development | Akanksha | 2 | 2 | Done |  | 0 | 0
Start Implementing Project | Interfaces | Arushi,Dhruva | 2 | 2 | Planned |  | 0 | 0
Team Meeting | Coordination | Dhruva,Siddharth,Ayush | 1 | 1 | Done |  | 0 | 0
Status Tracker | Documentation | All | 1 | 0.5 | Done
Week 8 (sept 22- sept 28)
Learn ROR | Preparation | All |  | 12 | Ongoing
Authentication | Development | Ayush | 2 | 3 | Basic Complete |  | -1 | 33.3333
Merge Codes | Merge | Siddharth | 1 | 2 | Done |  | -1 | 50
Marking cities | Development | Arushi, Dhruv | 4 | 6 | Ongoing |  | -2 | 33.3333
Team Meeting | Coordination | Arushi, Siddharth, Ayush | 1 | 1 | Done |  | 0 | 0
Status Tracker | Documentation | All | 1 | 1 | Done |  | 0 | 0
Plan Document | Documentation | Akanksha | 1 | 1 | Done |  | 0 | 0
Week 9(Sept 29 – Oct 5)
Learn ROR | Preparation | All |  | 6 | Ongoing
Plotting Cities | Development | Arushi, Siddharth |  | 4 | Ongoing
User interface | Development | Ayush, Dhruv |  | 4 | Ongoing
Design Document | Documentation | Siddharth, Akanksha | 1 | 4 | Done |  | -3 | 75
Status Tracker | Documentation | All | 1 | 1 | Done |  | 0 | 0
Team Meeting | Coordination | All | 1 | 1 | Done |  | 0 | 0
Week 10(Oct 6 - Oct 12)
City Database making | Development | Arushi, Akanksha |  | 9 | Done
Search cities based on parameters | Development | Arushi, Akanksha |  | 18 | Ongoing
User Interface | Development | Ayush, Dhruv, Siddharth | 9 | 17 | Ongoing |  | -8 | 47.0588
Google map API | Development | Siddharth | 12 | 22 | Ongoing |  | -10 | 45.4545
Status Tracker | Documentation | All | 5 | 5 | Done |  | 0 | 0
Revising docs | Documentation | Siddharth, Dhruv | 2 | 8 | Done |  | -6 | 75
Team meeting | Coordination | All |  | 6 | Done
Presentation Preparation | Preparation | All | 20 | 28 | Done |  | -8 | 28.5714
Week 11(Oct 13-19)
Team meeting | Coordination | All |  | 5 | Done
Presentation Preparation | Preparation | All | 12 | 15 | Done |  | -3 | 20
Week 12(Oct 20 - Oct 26)
Mid-Sem2(Oct 18-21)
Deepavali Break(Oct 22-26)
Week 13
Week 14
Week 15
Week 16
Week 17

## Individual_Status
TEAM NAME | SSAD_46
PROJECT NAME | SURROGATE CITY
PROJECT MENTOR | DR. VISHAL GARG
Actvities | ARUSHI VASHIST |  | AKANKSHA |  | SIDDHARTH |  | AYUSH TRIPATHI |  | DHRUVA DAS |  | Estimated Total Hours | Actual Total Hours
| Estimated Time | Actual Time Spent | Estimated Time | Actual Time Spent | Estimated Time | Actual Time Spent | Estimated Time | Actual Time Spent | Estimated Time | Actual Time Spent
Week 6 (sept 8- sept 14)
Learning basics of ROR | 2-3 hours |  | 2-3 hours |  | 4-5 hours | 3-4 hours | 3-4 hours | 4 1/2 - 5 hours | 3-4 hours | 4-4 1/2 hours | 15-20 hours | #VALUE!
Role preferences | 1 hour |  | 1 hour |  | 1 hour | 1 hour | 1 hour | 1 hour | 1 hour | 1 hour | 5 hours | #VALUE!
Bitbucket Repository | 30 minutes |  | 45 minutes |  | 45 minutes | 45 minutes | 45 minutes | 45 minutes | 45 minutes | 30 minutes | 3 hours 30 minutes | #VALUE!
#NAME? | 30 minutes |  | 30 minutes |  | 30 minutes | 30 minutes | 30 minutes | 40 minutes | 30 minutes | 45 minutes | 2 hours 30 minutes | #VALUE!
Develop Project plan Document | 1 hour |  | 1 hour |  | 1 hour | 1.5 hour | 1 hour | 1 hour | 1 hour | 1 hour 30 min | 2 hours 30 minutes | #VALUE!
Meet and Discuss requirements with client | 1 hour |  | 1 hour |  | 1 hour | 1 hour | 1 hour | 1 hour | 1 hour | 1 hour | 2 hours 30 minutes | #VALUE!
Research Technology | 1 hours |  | 2 hours |  | 3 hours | 2 hour | 1 hour and 30 minutes | 4-5 hours | 3 hours | 4 hours | 10 hours 30 minutes | #VALUE!
Project synopsis writeup | 40 minutes |  | 50-55 minutes |  | 1 hour | 45 minutes | 45 minutes | 1 hour | 45 minutes | 1 hour | 4 hours 15 minutes to 4 hours 20 minutes | #VALUE!
Identify role owners | 20 minutes |  | 20 minutes |  | 20 minutes | 20 minutes | 30 minutes | 30 minutes | 20 minutes | 20 minutes | 1 hour 50 minutes | #VALUE!
Team Meeting | 45 minutes |  | 45 minutes |  | 45 minutes | 45 minutes | 45 minutes | 45 minutes | 45 minutes | 1 hour | 3 hours 45 minutes | #VALUE!
Status tracker | 15 minutes |  | 15 minutes |  | 15 minutes | 45 minutes | 15 minutes | 15 minutes | 15 minutes | 30 minutes | 1 hour 15 minutes | #VALUE!
Week 7 (sept 15 - sept 21) | 0 | 0 | 0 | 0 | 0 | 0
Learning basics of ROR | 2-3 Hours | 4-5 Hours | 2-3 Hours | 4-5 hours | 2-3 hours | 4-5 hours | 3-4 hours | 7-8 hours | 3-4 hours | 4-5 hours | #VALUE! | #VALUE!
Testing Google Map API | 5-6 Hours | 8 Hours | 1 Hour | 1 Hour | [6 empty] | #VALUE! | #VALUE!
Fetching Data Files | 1 Hours | 1 Hour | 2-3 Hours | 4-5 hours | 1 hour | 2 hours |  |  | 1-2 hours | 2 hours | #VALUE! | #VALUE!
Making Database | 1 Hours | - |  |  |  |  | 2 hours |  |  |  | #VALUE! | 0
Refining knowledge of requirements | 2 Hours | 2 Hours | 2 Hours | 2 Hours | 2 hours | 3 hours | 2 hours | 3 hours | 2 hours | 3 hours | #VALUE! | #VALUE!
SRS Document |  |  | 2 Hours | 3 Hours | 2-3 hours | 6-7 hours | 3 hours | 5 hours | 2 hours | 4-5 hours | #VALUE! | #VALUE!
Team Meeting | 1 Hour | 1 Hours | 1 Hour | 1 Hours | 1 hour | 1 hour | 1 hour | 1 hour | 1 hour | 1 hour
Status Tracker | 15 minutes | 15 minutes | 15 minutes | 15 minutes | 15 minutes | 30 minutes | 30 minutes | 1 hours 30 minutes | 15 minutes | 45 minutes
Week 8 (sept 22- sept 28)
Learn ROR |  | 4 Hours |  | 2 Hours |  | 12 Hours |  | 4 Hours |  | 2 Hours | 0 | #VALUE!
Authentication | [6 empty] | 2 hours | 3 hours |  |  | #VALUE! | #VALUE!
Merge Codes |  |  |  |  | 1 hour | 2 hour |  |  |  |  | #VALUE! | #VALUE!
Marking cities | 4 hours | 6 hours | [6 empty] | 4 hours | 6 hours | #VALUE! | #VALUE!
Team Meeting | 1 hour | 1 Hour | 1 Hour | 1 Hour | 1 hour | 1 hour | 1 hour | 1 hour | 1 hour | 1 hour | #VALUE! | #VALUE!
Status Tracker | 1 hour | 1 Hour | 1 Hour | 1 Hour | 1 hour | 1 hour | 1 hour | 1 hour | 1 hour | 1 hour | #VALUE! | #VALUE!
Plan Document |  |  | 1 Hour | 1/2 hour | [6 empty] | #VALUE! | #VALUE!
[11 empty] | 0 | 0
Week 9(Sept 29 – Oct 5)
Learn ROR |  | 2 Hours |  | 2 Hours |  | 2 hour |  |  |  |  | 0 | #VALUE!
Plotting Cities |  | 3 Hours |  |  |  | 1 hours |  |  |  |  | 0 | #VALUE!
User interface | [7 empty] | 2 hours |  | 2 hours | 0 | #VALUE!
Design Document |  |  |  | 1 Hour | 4-5 hours | 4-5 hours |  |  |  |  | #VALUE! | #VALUE!
Status Tracker | 1 hour | 1 hour | 1 Hour | 1 hour | 1 hour | 1 hour | 1 hour | 1 hour | 1 hour | 1 hour | #VALUE! | #VALUE!
Team Meeting | 1 hour | 1 Hour | 1 Hour | 1 Hour | 1 hour | 1 hour | 1 hour | 1 hour | 1 hour | 1 hour | #VALUE! | #VALUE!
[11 empty] | 0 | 0
Week 10(Oct 6 - Oct 12) | Coordination | All | 0 | 5 | Done | 0 |  |  | 0 | 0 | 0 | 0
City Database making |  | 3 hours |  | 6 hours | [6 empty] | 0 | #VALUE!
Search cities based on parameters |  | 9 hours |  | 9 hours | [6 empty] | 0 | #VALUE!
User Interface |  |  |  |  | 1 hour | 1 hour | 4 hours | 8 hours | 4 hours | 8 hours | #VALUE! | #VALUE!
Google map API |  | 3 hours |  | 3 hours |  | 16 hours |  |  |  |  | 0 | #VALUE!
Status Tracker | 1 hour | 1 hour | 1 hour | 1 hour | 1 hour | 1 hour | 1 hour | 1 hour | 1 hour | 1 hour | #VALUE! | #VALUE!
Revising docs |  |  |  |  | 1 hour | 4 hours |  |  | 1 hour | 4 hours | #VALUE! | #VALUE!
Team meeting |  | 6 hours |  | 6 hours |  | 6 hours |  | 6 hours |  | 6 hours | 0 | #VALUE!
Presentation preparaion | 4 hours | 8 hours | 4 hours | 8 hours | 4 hours | 4 hours | 4 hours | 4 hours | 4 hours | 4 hours | #VALUE! | #VALUE!
Week 12(Oct 20 - Oct 26) | [10 empty] | 0 | 0
Mid-Sem2(Oct 18-21) | [10 empty] | 0 | 0
Deepavali Break(Oct 22-26) | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
Week 13 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
Week 14 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
Week 15 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
Week 16 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
Week 17 | [10 empty] | 0 | 0
Week 10(Oct 6 - Oct 12) | [10 empty] | 0 | 0
Presentation Preparation | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
Week 12(Oct 20 - Oct 26) | [10 empty] | 0 | 0
Mid-Sem2(Oct 18-21) | [10 empty] | 0 | 0
Deepavali Break(Oct 22-26) | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
Week 13 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
Week 14 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
Week 15 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
Week 16 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
Week 17 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0 | [10 empty] | 0 | 0
0